## PEARL Stage 2 Sign Off Sheet
PEARL - Stage 2 Sign Off Sheet
PEARL Board Sign Off
Name | Role | Signature of Stage 2 Sign Off | Date
Nigel Titchener Hooker
Nick Tyler
Sarah Collins
Neil Turvey
Tom Doubleday | UPO | T. Doubleday | 2018-04-29
UCL Estates Sign Off
Name | Role | Signature of Stage 2 Sign Off | Date

## PEARL Stage 2 Comments Tracker
Stage 2 Project Board Comments
Volume Number | Page Number | Raised By | Date Raised | Comment | Design Team Response
Board Presentation | Board Presentation | Nigel Titchener Hooker | 23.04.19 | Query regarding the understated design of the main entrance in to the new PEARL building, can this be reviewed during stage 3 to make for a more grand entrance | Design of entrance to be reviewed during stage three. Design of main entrance door somewhat impacted by M&E requirements of the space but will be reviewed further.
Board Presentation | Board Presentation | Hayden Velinor | 23.04.19 | Has thermal modelling been undertaking to ensure that comfortable temperature zones are achieved at various levels within the building? | Thermal modelling will be completed. The retractable seating does not extend above a height of 2-2.5m from ground level. This height will be considered in ensuring comfortable temperature zones. Movement of air in the building is required to be in accordance with strict acoustic requirements which pose design challenges
Board Presentation | Board Presentation | Jane (funder) | 23.04.19 | VAT recovery was mentioned as an opportunity for cost savings. It needs to be considered that VAT recovery could have an impact on building use in the long run in the form of charge out for certain projects. | UCL are working with their VAT consultant to understand the potential savings and implications associated with the VAT recovery. The implications will be fully considered before a decision is made. The Team propose to have this item closed out during Stage 3.
Fire Startegy |  | Nick Tyler | 23.04.19 | Sprinklers - Acknowledgement this requires further review to remove them from the scheme if possible, early during the next design stage. | Accepted. To be reviewed in Stage 3.
Architecture |  | Nick Tyler | 23.04.19 | Storage Containers - Change 40ft containers to 2nr 20ft containers | Accepted. To be updated in Stage 3.
Cost |  | Nick Tyler | 23.04.19 | Route back to budget items: 1. MEP items to be further clarified to determine if achievable and what they mean. 2. Auditable speakers - Accepted by NT, subject to building control approval. | Noted. All route back to budget items to be explored as a priority in RIBA stage 3.
Stage 2 UCL Estates Comments
Volume Number | Page Number | Raised By | Date Raised | Comment | Design Team Response